## Sheet1
Workflow rules | Invoice notification to Owner | Invoice notification to Owner - TWA | Invoice notification to queue | Invoice notification to queue-TWA | Resolution provided
Workflow Rule Status | Deactivated | Deactivated | Deactivated | Active
Flow | Part of flow | Part of flow | Part of flow | Not part of flow
Behaviour | Working as expected | Had issue | Had issues - Notification not going to Non-twa, and double notification to TWA
Fix Applied |  | Fixed by adding ISBLANK(CAH_Complete__c) in Flow | Notification not going to Non-twa- Added ISBLANK(CAH_Complete__c) in Flow Double Notification - Reproduced in SB, it was working fine, still changed the condition from TWA OR TWA OUS to TWA and WA OUS in Flow
For TWA – OUS Payment Failures && TWA-OUS , current state was getting affected due to global level change for invoice type |  |  |  |  | Bypassed TWA-OUS && TWA – OUS Payment Failures condition to not change state in trigger class
Present issue - In one scenario the Invoice is first routed to Amanda SIngh(2nd level Approver) to the BP first and then it is routed for CAH Supervisory approval. Doing so meant that when the Invoice in the CAH Supervisory approval state was approved by the 1st Level approver the Notification to the 2nd level approver Amanda got missed, however the invoice did not get autoapproved. |  |  |  |  | Fixed and currently auto approval working need some modifications
For price payback & system/aperror payback it goes for 2 level cora approval |  |  |  |  | Connected with ops team and clarified the flow for these two invoice type